## Slide 1
Secure Machine Learning with SQL Server ML Services
Contoso Secure Manufacturing

## Slide 2: Opportunity Statement
Contoso Secure Manufacturing creates and repairs components for highly secure solutions. We wish to create a Predictive Maintenance solution whereby we keep all data on-premises, but train a predictive model at a remote location. Sample, anonymized data must be used in the training.
Currently, all manufacturing steps record data into a SQL Server Instance
Ideally, the model created would be used in the testing phase of manufacturing for quality control, and also be deployable to an IoT device as an add-on service for the equipment once deployed.

## Slide 3: Goals and Objectives
Create an external Machine Learning (ML) Experiment process for Predictive Maintenance, using anonymized (but representative) data
Create and version models from the experimentation process
Import the model locally to a secure manufacturing/repair facility
Run a prediction using the model, over data stored in a SQL Server table
Stretch goal: Deploy the model to an IoT device for constant prediction in the field. Contoso can upcharge for this service

## Slide 4: Project Post-Mortem
Phase | Deliverable | Phase Notes
Discovery | Business Requirements | Generated multiple meetings with various stakeholders – Security team had full process for evaluation that we needed to follow
Envisioning | Business-Ready Presentation | Stakeholders wanted security assurances and project timelines
Architecture Design Session | Wireframe Diagram, Data Flow Diagram | Multiple options considered, primary decision points are around the on-premises decision, since the model can be generated anywhere.
Proof of Concept | Functional Prototype | Spent a lot of time with a candidate solution to show, found a good example.
Implementation | Project Oversight Document | Project timelines went more or less as expected, but two unplanned PTO events on critical team members had us lag expectations for a bit. We were able to regroup and recover the time.
Handoff | All previous documents, follow-up strategy document | Team is finalizing these artifacts, specifically the documentation team.

## Slide 5: Recommendations and Next Steps
The project met expectations
Retraining for “ground truth” needs to be tracked and put into place for proper model evolution (V2)
V2 should include enhanced reporting
V2 should include push to IoT for better customer sat, and for an additional revenue stream