## Sheet1
Task Summary Name | Name | Resource Names
Scope | Determine project scope | Management
Scope | Secure project sponsorship | Management
Scope | Define preliminary resources | Project Manager
Scope | Secure core resources | Project Manager
Scope | Scope complete
Analysis/Software Requirements | Conduct needs analysis | Analyst
Analysis/Software Requirements | Draft preliminary software specifications | Analyst
Analysis/Software Requirements | Develop preliminary budget | Project Manager
Analysis/Software Requirements | Review software specifications/budget with team | Project Manager,Analyst
Analysis/Software Requirements | Incorporate feedback on software specifications | Analyst
Analysis/Software Requirements | Develop delivery timeline | Project Manager
Analysis/Software Requirements | Obtain approvals to proceed (concept, timeline, budget) | Management,Project Manager
Analysis/Software Requirements | Secure required resources | Project Manager
Analysis/Software Requirements | Analysis complete
Design | Review preliminary software specifications | Analyst
Design | Develop functional specifications | Analyst
Design | Develop prototype based on functional specifications | Analyst
Design | Review functional specifications | Management
Design | Incorporate feedback into functional specifications | Management
Design | Obtain approval to proceed | Management,Project Manager
Design | Design complete
Development | Review functional specifications | Developer
Development | Identify modular/tiered design parameters | Developer
Development | Assign development staff | Developer
Development | Develop code | Developer
Development | Developer testing (primary debugging) | Developer
Development | Development complete
Testing | Develop unit test plans using product specifications | Testers
Testing | Develop integration test plans using product specifications | Testers
Unit Testing | Review modular code | Testers
Unit Testing | Test component modules to product specifications | Testers
Unit Testing | Identify anomalies to product specifications | Testers
Unit Testing | Modify code | Testers
Unit Testing | Re-test modified code | Testers
Unit Testing | Unit testing complete
Integration Testing | Test module integration | Testers
Integration Testing | Identify anomalies to specifications | Testers
Integration Testing | Modify code | Testers
Integration Testing | Re-test modified code | Testers
Integration Testing | Integration testing complete
Training | Develop training specifications for end users | Trainers
Training | Develop training specifications for helpdesk support staff | Trainers
Training | Identify training delivery methodology (computer based training, classroom, etc.) | Trainers
Training | Develop training materials | Trainers
Training | Conduct training usability study | Trainers
Training | Finalize training materials | Trainers
Training | Develop training delivery mechanism | Trainers
Training | Training materials complete
Documentation | Develop Help specification | Technical Communicators
Documentation | Develop Help system | Technical Communicators
Documentation | Review Help documentation | Technical Communicators
Documentation | Incorporate Help documentation feedback | Technical Communicators
Documentation | Develop user manuals specifications | Technical Communicators
Documentation | Develop user manuals | Technical Communicators
Documentation | Review all user documentation | Technical Communicators
Documentation | Incorporate user documentation feedback | Technical Communicators
Documentation | Documentation complete
Pilot | Identify test group | Project Manager
Pilot | Develop software delivery mechanism
Pilot | Install/deploy software | Deployment Team
Pilot | Obtain user feedback | Deployment Team
Pilot | Evaluate testing information | Deployment Team
Pilot | Pilot complete
Deployment | Determine final deployment strategy | Deployment Team
Deployment | Develop deployment methodology | Deployment Team
Deployment | Secure deployment resources | Deployment Team
Deployment | Train support staff | Deployment Team
Deployment | Deploy software | Deployment Team
Deployment | Deployment complete
Post Implementation Review | Document lessons learned | Project Manager
Post Implementation Review | Distribute to team members | Project Manager
Post Implementation Review | Create software maintenance team | Project Manager
Post Implementation Review | Post implementation review complete